## Sheet1
Dates | Goal
2021-10-06 | Midterm Presentation | Dates: | 2021-11-29 | Image Processing | Signal Processing | Route Planning | GUI | Motorized Mount | Antenna
|  | Image Processing |  | Program Outline | Program Outline | Program Outline | Program Outline | 3D models | 3D Model & Sim
|  | Program Outline |  | Create Test Data | Read in From SDR | Read Selection from GUI | Interacting with Skymap | Mathmatical Analysis | Manufacter Plan
|  | Create Test Data |  | Read in CSVs | Calculating Frequency and Magnitude | Account for Earths Rotation | Output to Route Planning | Controller Recivces from Route Planner | Single Element Protype & Verification
|  | Read in CSVs |  | Heat Map for 2-d Scan | Consolidate Data into CSVs | Map to Spherical | Input from Image Processing | Controller Outputs to Stepper Motors | Finalized Element Design
|  | Heat Map for 2-d Scan |  | Heat Map for 2-d Terrestrial | Send CSVs via Bluetooth | Route 2-d Scan |  | Controller Generates Movement | Phase Alignment
|  | Heat Map for 2-d Terrestrial |  | Heat Map for 1-D Terrestiral |  | Route 2-d Terrestrial |  | Linear Actuators | Signal Combined
|  | Heat Map for 1-D Terrestiral |  | Heat Map for RPA |  | Route 1-d Terrestrial |  | Prototype Finished | Array Assembled
|  | Heat Map for RPA |  | Image Overlay |  | Route RPA
|  | Image Overlay |  |  |  | Output Shperical Coordinates in CSVs
Signal Processing
Program Outline
Read in From SDR
Calculating Frequency and Magnitude
2021-10-25 | Projects Updates | Consolidate Data into CSVs
Send CSVs via Bluetooth
Route Planning
Program Outline
Read Selection from GUI
Account for Earths Rotation
Map to Spherical
Route 2-d Scan
Route 2-d Terrestrial
Route 1-d Terrestrial
2021-11-15 | Final Presentation | Route RPA
Output Shperical Coordinates in CSVs
GUI
2021-11-29 | Subsystem Demo | Program Outline
Interacting with Skymap
2021-12-05 | Final Report | Output to Route Planning
Input from Image Processing
Motorized Mount
3D models
Mathmatical Analysis
Build Linear Actuators
Prototype Finished
Controller Recivces from Route Planner
Controller Outputs to Stepper Motors
Controller Generates Movement
Antenna
3D Model & Sim
Manufacter Plan
Single Element Protype & Verification
Finalized Element Design
Finalized Element Construction
Phase Alignment
Array Assembled
Signal Combined